## Form Responses 1
Timestamp | Email Address | Name | Contact no. | Designation | Years Of Experience | Name and address of the organization | Related to | Name of the project | Status of the project | Total expected cost of the Project | Type of the Project | Have you come across cost overrun during handling any construction project? | Does the cost overrun delays the project? | mention causes of cost over run of your project and its impact [Improper cash inflow and outflow] | mention causes of cost over run of your project and its impact [Errors in designs] | mention causes of cost over run of your project and its impact [Delays in analysis & alteration in designs] | mention causes of cost over run of your project and its impact [Mismatch of ongoing construction with the actual plan] | mention causes of cost over run of your project and its impact [Increase in the cost of project] | mention causes of cost over run of your project and its impact [Conflict between owner and contractor] | mention causes of cost over run of your project and its impact [Changes in soil characteristics, at the time of construction] | mention causes of cost over run of your project and its impact [Incorrect Estimate] | mention causes of cost over run of your project and its impact [If owner is not financially viable] | mention causes of cost over run of your project and its impact [Issues relating to frauds and miscreants] | mention causes of cost over run of your project and its impact [Poor construction strategy] | mention causes of cost over run of your project and its impact [Poor site management] | mention causes of cost over run of your project and its impact [Enhancement in the cost of labourers] | mention causes of cost over run of your project and its impact [Unusual payment to labourers] | mention causes of cost over run of your project and its impact [Improper control of finance] | mention causes of cost over run of your project and its impact [Improper communication between owner and the contractor] | mention causes of cost over run of your project and its impact [Conflict on differentiating and biasing in between labourers] | mention causes of cost over run of your project and its impact [Improper material management and procurement] | mention causes of cost over run of your project and its impact [Accident due to faulty equipment] | mention causes of cost over run of your project and its impact [Non-availability of authorized (IS marked) machineries] | mention causes of cost over run of your project and its impact [Sudden fall of demand of a particular material in the market] | mention causes of cost over run of your project and its impact [Delivery of faulty machineries] | mention causes of cost over run of your project and its impact [Idle mindset of labourers] | mention causes of cost over run of your project and its impact [Improper maintenance of equipment] | mention causes of cost over run of your project and its impact [Changes in materials and labour] | mention causes of cost over run of your project and its impact [Demand of high prices by group of labourers] | mention causes of cost over run of your project and its impact [Rise and fall in prices of material] | mention causes of cost over run of your project and its impact [Failure of equipment at the time of construction] | mention causes of cost over run of your project and its impact [Price hike of materials] | mention causes of cost over run of your project and its impact [Hiring of unskilled labourers] | mention causes of cost over run of your project and its impact [Improper technical performance] | mention causes of cost over run of your project and its impact [Lack of technical assistance from the government] | mention causes of cost over run of your project and its impact [Wastes rising from construction materials] | mention causes of cost over run of your project and its impact [Existing demand in market] | mention causes of cost over run of your project and its impact [Less availability of living and food arrangements for labors.] | mention causes of cost over run of your project and its impact [Inadequate materials] | mention causes of cost over run of your project and its impact [Improper use of resources] | mention causes of cost over run of your project and its impact [Worker’s problems] | mention causes of cost over run of your project and its impact [Sudden increase in price of commodities] | mention causes of cost over run of your project and its impact [Less availability of time (time uncertainties).] | mention causes of cost over run of your project and its impact [Inaccurate project cost, which leads to confusion.] | mention causes of cost over run of your project and its impact [New additional works, which gave rise to increased problems] | mention causes of cost over run of your project and its impact [Problems pertaining to environmental clearance] | mention causes of cost over run of your project and its impact [Unpredictable circumstances (flood, cyclone, earthquake etc)] | mention causes of cost over run of your project and its impact [COVID-19 pandemic] | mention causes of cost over run of your project and its impact [Levies or taxes charged by the agencies] | mention causes of cost over run of your project and its impact [Local people/political interference] | mention causes of cost over run of your project and its impact [Unsuitable weather conditions] | What are the steps taken to over come the cost overrun? | Any suggestion to overcome the cost overrun
2021-11-24 21:35 | pinkynayak183@gmail.com | Pinky Nayak | 9090937668 | Stores Accountant | 2 years | Odisha Secretariat | Owner | Jeypore-Nabrangpur railway project (42 kilometers) | Ongoing | 738 crores | Railway Projects | Yes | Yes | Extreme | Little | Moderate | Moderate | High | Moderate | High | Extreme | Extreme | Very little | Little | Little | High | High | Extreme | Extreme | Little | Little | Extreme | Extreme | Moderate | Little | Little | Moderate | Extreme | Very little | Very little | Moderate | High | Little | Moderate | Moderate | Very little | Little | Little | Moderate | High | Moderate | Extreme | Moderate | High | Extreme | Extreme | Extreme | High | High | Moderate | High | 1.A proper management of materials, laborers and finance, 2. Completing the project within a stipulated time and cost, 3. Abiding to laws and regulations as proposed by the government. | Same as above.
2021-11-24 21:59 | vikas980@gmail.com | Vikash Pattnaik | 9775606327 | Junior engineer | 1 years | Works Department, Govt. of Odisha | Contractor | Construction of a minor culvert at Khorda bypass road | Completed | 17.44 lakhs | Bridge Projects | Yes | Yes | Extreme | High | High | Extreme | Extreme | Extreme | Little | Extreme | High | Extreme | High | Very little | Very little | Moderate | High | Little | Moderate | High | Extreme | Extreme | Very little | Little | Moderate | Extreme | High | Moderate | Extreme | Very little | Moderate | Very little | Little | Little | High | Extreme | High | Moderate | Extreme | Little | Extreme | Little | High | Very little | Extreme | Moderate | Extreme | High | Moderate | Extreme | A combined trail should be proposed by the contractor to take Care of all the problems likely to happen in a project. | Same as above.
2021-11-25 14:46 | se@aiimsbhubaneswae.edu.in | Kali Prasad Mishra | 9437319398 | Superintending Engineer | 5+ years | AIIMS, BHUBANESWAR | Contractor | Construction of Aayush building at AIIMS premises | Completed | 67 crores | Building Projects | Yes | Yes | Moderate | Extreme | Moderate | Little | Extreme | Extreme | Extreme | High | Extreme | Moderate | Little | Little | Little | Moderate | Very little | Moderate | Moderate | Little | Extreme | Moderate | High | Extreme | Extreme | Very little | High | Moderate | High | Extreme | Extreme | Very little | Very little | Very little | Moderate | High | Moderate | Extreme | Little | Moderate | Extreme | Extreme | High | Very little | Extreme | Moderate | Extreme | Little | High | High | A significant study suggests that, cost overrun mainly occurs due to all the above defined problem. We can make good choices of materials, laborers, have a good attitude and strategy towards the project and should try our best to complete the project within a given time, irrespective of conditions.
2021-11-25 19:33 | ankita01cpwd@gmail.com | Ankita Sahu | 7008491407 | Junior Engineer | 1 years | Central Public Works Department | Contractor | Construction of a 3 storey office complex at GSI worksite. | Ongoing | 43.87 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Little | Little | Extreme | High | Extreme | High | Very little | Little | High | Extreme | Extreme | Moderate | High | Extreme | Moderate | Extreme | Moderate | Extreme | Extreme | High | Extreme | Little | High | Moderate | High | Extreme | Extreme | Little | Very little | High | Moderate | High | Extreme | Extreme | Little | High | High | Extreme | Very little | High | Moderate | Extreme | Very little | Moderate | Little | New as well as good quality of materials should be hired. Skilled laborers with sound technical knowledge are also important for a successful completion of project.
2021-11-27 11:21 | pkmohantyae@cpwd.gov.in | Pramod Kumar Mohanty | 9438166062 | Assistant Engineer | 5 and above | Central Public Works Department, Bhubaneswar Region | Contractor | Construction of a G+3 office building | Ongoing | 44 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | Moderate | Little | High | Moderate | Little | Extreme | Extreme | Moderate | High | Little | Extreme | Extreme | High | Extreme | High | Extreme | Extreme | Moderate | High | High | Extreme | Extreme | Extreme | Moderate | Very little | Moderate | Very little | Extreme | High | Very little | Extreme | High | Extreme | Moderate | Extreme | High | Moderate | Little | Moderate | High | A cost-effective planning as well as a good construction method is required to reduce the bad effect of cost overrun.
2021-11-28 11:59 | bpmishra1976@gmail.com | Bhabani Prasad Mishra | 9437014612 | Senior Project Engineer | 5 and above | Z Estates, Patia, Bhubaneswar | Owner | Construction of a sub-urban apartment near Sainik School, Bhubaneswar | Ongoing | 58 crores | Building Projects | Yes | Yes | High | Extreme | Extreme | Extreme | Extreme | Moderate | High | Extreme | Extreme | Very little | Moderate | Little | High | Moderate | High | Little | Extreme | Extreme | High | Extreme | Extreme | Extreme | Moderate | High | High | Extreme | Extreme | Extreme | High | Extreme | Little | Very little | Moderate | Moderate | High | Extreme | Extreme | Little | Extreme | High | Extreme | Very little | Extreme | High | High | Little | Moderate | Moderate | A careful selection of work site, materials, equipments and labor is required to reduce cost overrun. Proper flow of cash and words of encouragement to the laborers are also effective tools for reducing the loss to the organization. | Same as previous.
2021-11-28 19:55 | skdash75@kiit.ac.in | Sashikanta Dash | 9807685988 | Registrar | 9 years | KIIT School of Management | Owner | Renewal of central smart learning building | Ongoing | 38 crores | Building Projects | Yes | Yes | Extreme | High | Extreme | Extreme | High | Moderate | High | Extreme | Extreme | Little | Extreme | Moderate | Moderate | High | Extreme | High | Moderate | Little | Extreme | Extreme | Extreme | High | Moderate | High | Little | Moderate | High | High | Extreme | Extreme | Very little | Little | Moderate | Moderate | High | Moderate | High | Moderate | High | High | Extreme | Moderate | Extreme | High | High | Little | High | Little | As reconstruction of a structure is a difficult process, so we should be very careful while executing the constructional as well as aesthetical works. The main plan to avoid cost overrun should be a good planning and engagement of all resources and materials. | First, we should make the use of natural and locally available resources to get rid of extra cost of materials. Secondly, we should act by the laws given by government to safeguard our project from penalty.
2021-12-01 12:54 | sureshroutray77@gmail.com | Suresh Mohan Routray | 9668134739 | Estates Officer | 4 years | Paradip Port Trust | Contractor | Construction of residential buildings at IOCL campus, Paradip | Ongoing | 66.73 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Extreme | Extreme | Moderate | High | Extreme | High | High | Extreme | Extreme | Very little | Moderate | Moderate | High | High | Extreme | Extreme | High | Extreme | Moderate | High | Extreme | Extreme | Extreme | High | High | Extreme | High | Extreme | Extreme | Moderate | Little | Little | Moderate | High | Very little | Extreme | High | Extreme | Extreme | Extreme | Moderate | Moderate | High | Little | High | Timely delivery of materials, proper estimation of items of construction, non delay working are some of the major effective steps to control cost overrun | Same as before
2021-12-04 10:30 | girijam@lntechh.com | Girija Shankar Mohapatra | 8763354983 | Architectural Engineer | 5 and above years | Larsen & Tourbo Technologies, Nagpur. | Owner | Renovation and reconstruction of a multi-purpose office building | Ongoing | 37.72 crores | Building Projects | Yes | Yes | Extreme | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | High | Little | High | High | Extreme | Extreme | High | Extreme | High | Moderate | High | High | Extreme | High | Moderate | Extreme | High | Extreme | Extreme | Extreme | Extreme | High | Extreme | Moderate | High | High | Moderate | Little | Moderate | Very little | High | High | Moderate | Little | High | High | Moderate | Little | Little | Moderate | Due to advancement of technology and resources, we can make the use of good materials, skilled technical laborers, we should maintain a technical report in which the estimated cost and time of commencement add well as time of completion of the project is clearly mentioned.
2021-12-05 09:56 | rrmohapatra.ppt@yahoo.co.in | Rashmi Rani Mohapatra | 8895965407 | Senior Architect | 5 and above years | Planning and Design Cell, Paradip Port Trust | Owner | Setting up of the 100 million building at UP school premises | Completed | 46 crores | Building Projects | Yes | Yes | Extreme | High | High | Extreme | Extreme | High | Extreme | Extreme | Moderate | Little | High | Extreme | Extreme | Moderate | High | Moderate | Moderate | Moderate | Extreme | High | Extreme | High | High | Little | Moderate | High | Moderate | Extreme | High | Extreme | Extreme | Extreme | High | High | Extreme | High | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | Moderate | High | Extreme | Little | Extreme | A good planning and maintenance of materials and all resources, a proper strategy must be prepared to overcome the cost overrun in firms.
2021-12-05 10:08 | dashcr@owssb.gov.in | Chitta Ranjan Dash | 9114724094 | Technical Supervisor | 3 years | Odisha Water Supply & Sewerage Board, Bhubaneswar | Contractor | Construction of a sewage purifier plan at puri | Completed | 2.65 Lakhs | Water Resource Projects | Yes | Yes | Moderate | High | Extreme | High | Extreme | Extreme | High | High | High | Extreme | High | High | Moderate | Extreme | Extreme | High | Extreme | Extreme | Moderate | Moderate | Extreme | Extreme | Moderate | Very little | Moderate | Little | Extreme | High | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | Extreme | Extreme | Moderate | Moderate | High | Extreme | Moderate | Extreme | High | Moderate | Little | High | Extreme | A proper planning and designs of the structure to be constructed is important. The estimated cost of the construction along with necessary precautions are also necessary for the safety of workers and also to tackle overrun.
2021-12-05 11:20 | paritosj.osl@gmail.com | Paritosh Jena | 6370619926 | Site Engineer | 5 and above years | Orissa Stevedores Limited | Contractor | Construction of private jetty at gopalpur port | Ongoing | 32 crores | Water Resource Projects | Yes | Yes | High | Extreme | High | High | Extreme | Extreme | Extreme | Extreme | Moderate | High | Extreme | High | Extreme | Moderate | Little | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | High | Extreme | High | Extreme | Extreme | High | High | Moderate | High | Moderate | Little | High | High | Extreme | Extreme | Little | Extreme | High | Extreme | Moderate | Extreme | High | High | Moderate | Moderate | Extreme | The supervisors must check the progress of the project at regular intervals. We must encourage the fellow laborers to give their best and should keep them away from idleness as this can seriously affect the completion of a project. | Same
2021-12-05 18:32 | em@bdabbsr.in | Rama Ballav Swain | 9437195151 | Chief Engineer-cum-Engineer Member | 5 and above years | Bhubaneswar Smart City Limited. | Owner | Construction of International state bus terminal at Baramunda, Bhubaneswar | Ongoing | 180 crores | Building Projects | Yes | Yes | High | Extreme | Extreme | Extreme | High | High | Extreme | Extreme | Extreme | Little | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | Extreme | High | High | High | High | Moderate | High | High | Extreme | Extreme | Extreme | Moderate | Little | Moderate | High | High | Extreme | Extreme | High | Extreme | Moderate | Extreme | Extreme | Extreme | High | Extreme | Moderate | High | Little | High | Extreme | 1. We should plan and manage our resources according to the need of the project, 2. Tasks must be scheduled and organized in a strintgent manner, and 3.Control scope creep and optimize resources.
2022-02-14 11:14 | hrudananda.81@gmail.com | Hrudananda Majhi | 9937739905 | Technical Consultant | 5 and above years | Government of Odisha | Consultant | Construction of Buildings | Completed | 15 | Building Projects | Yes | No | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Little | Little | Very little | Very little | Little | Little | Little | Very little | Little | Little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Little | Very little | The projects should complete with in time period | Completed as per stipulated time
2022-02-14 11:16 | samal.manas@yahoo.com | Manas Ranjan Samal | 7894428577 | Director | 5 and above years | B.B. Infra solutions pvt.Ltd | Contractor | Widening and strenthening of sea beach road at Puri | Completed | 11 crores | Road Projects | Yes | Yes | Moderate | Moderate | Extreme | Extreme | High | Moderate | Moderate | High | Moderate | Moderate | High | Extreme | High | Moderate | High | Moderate | Moderate | High | High | Moderate | High | Moderate | Moderate | Moderate | Moderate | High | High | High | Extreme | High | High | High | Moderate | High | Moderate | High | High | Moderate | Moderate | High | High | Extreme | Extreme | Extreme | Extreme | High | High | High | Project management Material management Manpower management Equipment management Time management And finance management are the key features to overcome the cost overrun. | Steps should be taken to complete the project within the stipulated timeline with proper management.
2022-02-14 19:15 | jagatkumarswain2@gmail.com | Jagat kumar swain | 9658674026 | Structural engineer | 5 years | Sr engineering | Consultant | ITER mega hostel | Completed | 5crores | Building Projects | Yes | Yes | Little | Very little | Very little | Little | Moderate | Moderate | Little | Little | Very little | Very little | Little | Little | Little | Moderate | Moderate | Little | Very little | Moderate | Moderate | Very little | Very little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Little | Little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Moderate | Moderate | Little | Very little | Very little | Very little | Very little | Little | Very little | Proper coordination between the owner with construction company and structural consultant
2022-02-14 20:45 | nayakankit7@gmail.com | Ankit nayak | 8093367462 | Director | 5 years | Whiteant Buildoneers Pvt ltd | Owner | Construction of a G+3 Residential building over an area of 4000 sqft | Completed | 18000000 | Building Projects | Yes | Yes | Extreme | Very little | Very little | Moderate | Moderate | Little | Very little | High | Extreme | Little | Extreme | High | Little | Very little | High | Little | Moderate | High | Little | Very little | Extreme | Little | Very little | Moderate | Little | Moderate | High | Moderate | High | Moderate | Extreme | High | Little | Very little | Moderate | Very little | Moderate | High | Little | High | High | High | Little | Extreme | Extreme | Moderate | Moderate | High | Deal with clients and mutually solved the problem and strong management
2022-02-27 09:53 | kanhadash9124@gmail.com | kanha Dash | 9124641818 | Contractor | 5 and above years | KDCL | Contractor | Community Centre | Completed | 272000 | Building Projects | Yes | Yes | Little | Very little | Very little | Very little | Moderate | Very little | Very little | Little | Very little | Very little | Little | Very little | Moderate | Very little | Little | Very little | Very little | Very little | Very little | Very little | Little | Moderate | Very little | Little | Little | Little | Moderate | Little | Extreme | Little | Very little | Very little | Very little | Little | Little | Very little | Very little | Very little | High | Moderate | Extreme | Moderate | Moderate | Little | Extreme | Moderate | High | Very little | any sort of expense that pushes a project past the agreed-upon budget. | This is due to bad estimates, or not enough data being collected when formulating the budget.
2022-03-02 10:12 | ramahwp@gmail.com | RAMA KRISHNA BISWAL | 9437507791 | SCIENTIFIC OFFICER / F (CIVIL) | 5 and above years | HEAVY WATER PLANT BARODA, DEPARTMENT OF ATOMIC ENERGY, GOVT OF INDIA PO. FERTILIZER NAGAR, VADODARA GUJARAT 391750 | Owner | CONSTRUCTION OF SODIUM METAL PLANT AT BARODA. | Completed | 6,00,00,000/- | Building Projects | Yes | Yes | Very little | Little | High | Very little | Little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | High | Very little | Very little | Very little | Final Construction drawings released in time, alteration in design minimized. | All requirements should be finalized before commencement of construction, according to the requirement construction drawings to be prepared and should be released to the contractor in time. Particularly in industrial projects lot of modification comes from other interlinked sections. So to comply these demands drawings amended during progress of work.
2022-03-02 10:19 | rkpatel58@gmail.com | Rajan Patel | 9558729691 | Partner | 5 and above years | Somnath construction co | Contractor | National High Speed Rail Corporation Limited | Ongoing | 1.00 cr | Railway Projects | No | No | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | NA
2022-03-04 16:49 | ramahwp@gmail.com | RAMA KRISHNA BISWAL | 9437507791 | SCIENTIFIC OFFICER/F (CIVIL) | 5 and above years | HEAVY WATER PLANT TALCHER, DEPARTMENT OF ATOMIC ENERGY, GOVT OF INDIA | Owner | CIVIL & STRUCTURAL WORK FOR EFFLUENT TREATMENT PLANT AT HWP TALCHER. | Completed | 2.2 CRORE | Water Resource Projects | Yes | Yes | Very little | Little | Moderate | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | High | Very little | Very little | Very little | Very little | Very little | Very little | ADDITIONAL WORK RESTRICTED TO MINIMUM REQUIRED QUANTITY. | SCOPE OF WORK SHOULD BE FINALIZED DURING ADMINISTRATIVE APPROVAL STAGE, ACCORDINGLY SCHEDULE OF QUANTITY SHOULD BE PREPARED, SO THAT ADDITIONAL WORK CAN BE MINIMIZED.
2022-03-23 12:40 | asishsamantaray14469@gmail.com | Asish samantaray | 7381064714 | Site engineer | 5 and above years | Group G | Consultant | Grand bazar | Ongoing |  | Building Projects | No | No | High | Very little | Very little | Very little | Little | High | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Moderate | Little | Little | Moderate | Moderate | Moderate | Little | Little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Very little | NA | NA
2022-03-26 12:24 | mahliksatyabrta8@gmail.com | Satyabrata mahalik | 8018058028 | Design Engineer | 5 years | Group G | Consultant | Grand Awas | Ongoing | Dont Know | Building Projects | No | No | Little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Little | Little | Moderate | Little | Very little | Little | Very little | Very little | Little | Little | Very little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Very little | Little | Little | Very little | Little | Little | Little | Very little | Little | Very little | Very little | NA | NA
2022-03-30 08:40 | tender@lcepl.com | Satyashiva Dash | +917077826864 | Assistant Manager | 5 and above years | Laxmi civil Engineering Services Private Limited | Consultant | RWSS Mega Project | Ongoing | 322.34 Cr | Water Resource Projects | No | Yes | Very little | Very little | Very little | Little | Little | Very little | Moderate | Little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Moderate | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | High | Little | High | Moderate | Little | Little | Little | Very little | Little | Very little | Very little | Little | Very little | Little | Little | Little | Little | Very little | Little | Very little | Little | Very little | To Avoid Unskilled Labour | Labour should be skilled
2022-03-30 08:50 | dashswagat1993@gmail.com | Swagat Kumar Dash | +917377718694 | AEE(Panchayat Raj) | 1 year | Panchayat Raj Department Odisha Government | Consultant | Basudha | Completed | 1.39cr | Water Resource Projects | No | No | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Little | Very little | Little | Little | High | Little | Little | Very little | Very little | Very little | Little | Very little | Little | Moderate | Very little | Extreme | Little | Moderate | Little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Moderate | Very little | Little | Very little | Moderate | Little | Moderate | Moderate | Very little | High | Very little | NA | NA
2022-04-01 20:25 | biswajittlh@gmail.com | Biswajit Mohapatra | 6370150139 | Site engineer | 5 and above years | G-group construction | Consultant | Grand awas building | Ongoing | 423.27cr | Building Projects | No | No | Moderate | Moderate | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Moderate | Very little | Moderate | Very little | Little | Very little | Little | Very little | Very little | Very little | Little | Little | High | Moderate | High | Very little | Very little | Moderate | Moderate | Moderate | Very little | Very little | Very little | Very little | Moderate | Little | Very little | Little | Moderate | Very little | Moderate | Little | Very little | Very little | Thorough Project Planning. The best way to stop cost overrun is to plan against it before executing a project. ... | Quality and keeping to a schedule can all go out the window if the project is delivered over-budget.
2022-04-03 14:08 | sandeeplaskar858@gmail.com | SANDEEP LASKAR | 8249971807 | SITE ENGINEER | 5 and above years | G GROUP | Consultant | GRAND AWAS | Ongoing | 423 cr | Building Projects | No | No | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Little | Little | Very little | Little | Very little | Very little | High | Very little | High | Little | Very little | Very little | Little | Little | Very little | Very little | Very little | Very little | Moderate | Extreme | Very little | Very little | Very little | Very little | Moderate | Very little | High | Little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
2022-04-05 09:09 | ajayaempire@gmail.com | A K Mahapatra | 6372271891 | Contractor | 5 and above years | Smruti Construction | Contractor | Community center | Ongoing | 900000 | Building Projects | No | No | Moderate | Very little | Very little | Little | Little | Very little | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Extreme | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
2022-04-05 09:16 | rajcommunicationngr@gmail.com | BHIKARI PRADHAN | 8917552551 | Contractor | 5 and above years | Raj construction | Contractor | Drainage work | Ongoing | 700000 | Others | No | No | Very little | Very little | Very little | Very little | Little | Very little | Little | Very little | Very little | Little | Little | Very little | Moderate | Very little | Very little | Moderate | Very little | Very little | Very little | Little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Moderate | Moderate | Very little | Very little | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | The best way ti stop cost overrun is a plan against it before executing a project | Throughly plan your project ahead of time
2022-04-05 09:35 | bidharpritam@gmail.com | Pritam Bidhar | 6370855884 | Contractor | 3 years | Shakti builders | Contractor | Sri maa construction | Ongoing | 8000000 | Building Projects | No | No | Little | Little | Moderate | Little | Moderate | Moderate | Little | Little | Moderate | Little | Moderate | Little | Little | Moderate | Little | Little | Moderate | Little | Moderate | Little | Moderate | Moderate | Moderate | Moderate | Little | Moderate | Moderate | Moderate | Little | Moderate | Little | Moderate | Little | Little | Moderate | Little | Moderate | Little | Moderate | Little | Moderate | Little | Moderate | Moderate | Little | Moderate | Little | Moderate | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
2022-04-05 16:50 | sandeeptapatra2001@gmail.com | S K Patra | 6370109123 | Contractor | 5 and above years | Basanti construction,Balasore | Contractor | 2 lane railway bridge | Ongoing | 6,00,00,000 | Bridge Projects | Yes | Yes | Moderate | Very little | High | Moderate | Extreme | Extreme | Extreme | Little | Moderate | Very little | Very little | Very little | Extreme | Extreme | Extreme | Extreme | High | Little | Little | High | Extreme | Little | Extreme | Very little | Very little | Extreme | Extreme | Extreme | Extreme | Little | Moderate | High | Little | Moderate | Very little | Extreme | Extreme | Extreme | Extreme | Extreme | Little | Extreme | Little | Moderate | Extreme | Little | High | High | The best way to stop cost overrun is to plan against it before executing a project. Proper cost management. Hiring a good project manager. | Thoroughly plan your project ahead of time
2022-04-06 08:47 | amlantarai2000@gmail.com | Amlan Tarai | 7978085667 | Contractor | 5 and above years | S.K Construction | Contractor | Building & Apartment Projects | Ongoing | 16.86 cr | Building Projects | No | No | Little | Very little | Very little | Very little | Moderate | Little | High | Moderate | Little | Very little | Little | Very little | Moderate | Very little | Very little | Little | Very little | Moderate | Very little | Moderate | Moderate | Moderate | Little | Little | Little | Moderate | Little | Moderate | Moderate | Little | Little | Little | Very little | Moderate | Moderate | Little | High | Moderate | High | High | Moderate | High | High | Moderate | Little | Very little | Little | Little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time

## Sheet1
| Name | Related to | Status of the project | Total expected cost of the Project | Type of the Project | Have you come across cost overrun during handling any construction project? | Does the cost overrun delays the project? | mention causes of cost over run of your project and its impact [Improper cash inflow and outflow] | mention causes of cost over run of your project and its impact [Errors in designs] | mention causes of cost over run of your project and its impact [Delays in analysis & alteration in designs] | mention causes of cost over run of your project and its impact [Mismatch of ongoing construction with the actual plan] | mention causes of cost over run of your project and its impact [Increase in the cost of project] | mention causes of cost over run of your project and its impact [Conflict between owner and contractor] | mention causes of cost over run of your project and its impact [Changes in soil characteristics, at the time of construction] | mention causes of cost over run of your project and its impact [Incorrect Estimate] | mention causes of cost over run of your project and its impact [If owner is not financially viable] | mention causes of cost over run of your project and its impact [Issues relating to frauds and miscreants] | mention causes of cost over run of your project and its impact [Poor construction strategy] | mention causes of cost over run of your project and its impact [Poor site management] | mention causes of cost over run of your project and its impact [Enhancement in the cost of labourers] | mention causes of cost over run of your project and its impact [Unusual payment to labourers] | mention causes of cost over run of your project and its impact [Improper control of finance] | mention causes of cost over run of your project and its impact [Improper communication between owner and the contractor] | mention causes of cost over run of your project and its impact [Conflict on differentiating and biasing in between labourers] | mention causes of cost over run of your project and its impact [Improper material management and procurement] | mention causes of cost over run of your project and its impact [Accident due to faulty equipment] | mention causes of cost over run of your project and its impact [Non-availability of authorized (IS marked) machineries] | mention causes of cost over run of your project and its impact [Sudden fall of demand of a particular material in the market] | mention causes of cost over run of your project and its impact [Delivery of faulty machineries] | mention causes of cost over run of your project and its impact [Idle mindset of labourers] | mention causes of cost over run of your project and its impact [Improper maintenance of equipment] | mention causes of cost over run of your project and its impact [Changes in materials and labour] | mention causes of cost over run of your project and its impact [Demand of high prices by group of labourers] | mention causes of cost over run of your project and its impact [Rise and fall in prices of material] | mention causes of cost over run of your project and its impact [Failure of equipment at the time of construction] | mention causes of cost over run of your project and its impact [Price hike of materials] | mention causes of cost over run of your project and its impact [Hiring of unskilled labourers] | mention causes of cost over run of your project and its impact [Improper technical performance] | mention causes of cost over run of your project and its impact [Lack of technical assistance from the government] | mention causes of cost over run of your project and its impact [Wastes rising from construction materials] | mention causes of cost over run of your project and its impact [Existing demand in market] | mention causes of cost over run of your project and its impact [Less availability of living and food arrangements for labors.] | mention causes of cost over run of your project and its impact [Inadequate materials] | mention causes of cost over run of your project and its impact [Improper use of resources] | mention causes of cost over run of your project and its impact [Worker’s problems] | mention causes of cost over run of your project and its impact [Sudden increase in price of commodities] | mention causes of cost over run of your project and its impact [Less availability of time (time uncertainties).] | mention causes of cost over run of your project and its impact [Inaccurate project cost, which leads to confusion.] | mention causes of cost over run of your project and its impact [New additional works, which gave rise to increased problems] | mention causes of cost over run of your project and its impact [Problems pertaining to environmental clearance] | mention causes of cost over run of your project and its impact [Unpredictable circumstances (flood, cyclone, earthquake etc)] | mention causes of cost over run of your project and its impact [COVID-19 pandemic] | mention causes of cost over run of your project and its impact [Levies or taxes charged by the agencies] | mention causes of cost over run of your project and its impact [Local people/political interference] | mention causes of cost over run of your project and its impact [Unsuitable weather conditions] | What are the steps taken to over come the cost overrun? | Any suggestion to overcome the cost overrun
1 | Pinky Nayak | Owner | Ongoing | 738 crores | Railway Projects | Yes | Yes | Extreme | Little | Moderate | Moderate | High | Moderate | High | Extreme | Extreme | Very little | Little | Little | High | High | Extreme | Extreme | Little | Little | Extreme | Extreme | Moderate | Little | Little | Moderate | Extreme | Very little | Very little | Moderate | High | Little | Moderate | Moderate | Very little | Little | Little | Moderate | High | Moderate | Extreme | Moderate | High | Extreme | Extreme | Extreme | High | High | Moderate | High | 1.A proper management of materials, laborers and finance, 2. Completing the project within a stipulated time and cost, 3. Abiding to laws and regulations as proposed by the government. | Same as above.
2 | Vikash Pattnaik | Contractor | Completed | 17.44 lakhs | Bridge Projects | Yes | Yes | Extreme | High | High | Extreme | Extreme | Extreme | Little | Extreme | High | Extreme | High | Very little | Very little | Moderate | High | Little | Moderate | High | Extreme | Extreme | Very little | Little | Moderate | Extreme | High | Moderate | Extreme | Very little | Moderate | Very little | Little | Little | High | Extreme | High | Moderate | Extreme | Little | Extreme | Little | High | Very little | Extreme | Moderate | Extreme | High | Moderate | Extreme | A combined trail should be proposed by the contractor to take Care of all the problems likely to happen in a project. | Same as above.
3 | Kali Prasad Mishra | Contractor | Completed | 67 crores | Building Projects | Yes | Yes | Moderate | Extreme | Moderate | Little | Extreme | Extreme | Extreme | High | Extreme | Moderate | Little | Little | Little | Moderate | Very little | Moderate | Moderate | Little | Extreme | Moderate | High | Extreme | Extreme | Very little | High | Moderate | High | Extreme | Extreme | Very little | Very little | Very little | Moderate | High | Moderate | Extreme | Little | Moderate | Extreme | Extreme | High | Very little | Extreme | Moderate | Extreme | Little | High | High | A significant study suggests that, cost overrun mainly occurs due to all the above defined problem. We can make good choices of materials, laborers, have a good attitude and strategy towards the project and should try our best to complete the project within a given time, irrespective of conditions.
4 | Ankita Sahu | Contractor | Ongoing | 43.87 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Little | Little | Extreme | High | Extreme | High | Very little | Little | High | Extreme | Extreme | Moderate | High | Extreme | Moderate | Extreme | Moderate | Extreme | Extreme | High | Extreme | Little | High | Moderate | High | Extreme | Extreme | Little | Very little | High | Moderate | High | Extreme | Extreme | Little | High | High | Extreme | Very little | High | Moderate | Extreme | Very little | Moderate | Little | New as well as good quality of materials should be hired. Skilled laborers with sound technical knowledge are also important for a successful completion of project.
5 | Pramod Kumar Mohanty | Contractor | Ongoing | 44 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | Moderate | Little | High | Moderate | Little | Extreme | Extreme | Moderate | High | Little | Extreme | Extreme | High | Extreme | High | Extreme | Extreme | Moderate | High | High | Extreme | Extreme | Extreme | Moderate | Very little | Moderate | Very little | Extreme | High | Very little | Extreme | High | Extreme | Moderate | Extreme | High | Moderate | Little | Moderate | High | A cost-effective planning as well as a good construction method is required to reduce the bad effect of cost overrun.
6 | Bhabani Prasad Mishra | Owner | Ongoing | 58 crores | Building Projects | Yes | Yes | High | Extreme | Extreme | Extreme | Extreme | Moderate | High | Extreme | Extreme | Very little | Moderate | Little | High | Moderate | High | Little | Extreme | Extreme | High | Extreme | Extreme | Extreme | Moderate | High | High | Extreme | Extreme | Extreme | High | Extreme | Little | Very little | Moderate | Moderate | High | Extreme | Extreme | Little | Extreme | High | Extreme | Very little | Extreme | High | High | Little | Moderate | Moderate | A careful selection of work site, materials, equipments and labor is required to reduce cost overrun. Proper flow of cash and words of encouragement to the laborers are also effective tools for reducing the loss to the organization. | Same as previous.
7 | Sashikanta Dash | Owner | Ongoing | 38 crores | Building Projects | Yes | Yes | Extreme | High | Extreme | Extreme | High | Moderate | High | Extreme | Extreme | Little | Extreme | Moderate | Moderate | High | Extreme | High | Moderate | Little | Extreme | Extreme | Extreme | High | Moderate | High | Little | Moderate | High | High | Extreme | Extreme | Very little | Little | Moderate | Moderate | High | Moderate | High | Moderate | High | High | Extreme | Moderate | Extreme | High | High | Little | High | Little | As reconstruction of a structure is a difficult process, so we should be very careful while executing the constructional as well as aesthetical works. The main plan to avoid cost overrun should be a good planning and engagement of all resources and materials. | First, we should make the use of natural and locally available resources to get rid of extra cost of materials. Secondly, we should act by the laws given by government to safeguard our project from penalty.
8 | Suresh Mohan Routray | Contractor | Ongoing | 66.73 crores | Building Projects | Yes | Yes | Moderate | High | Extreme | Extreme | Extreme | Moderate | High | Extreme | High | High | Extreme | Extreme | Very little | Moderate | Moderate | High | High | Extreme | Extreme | High | Extreme | Moderate | High | Extreme | Extreme | Extreme | High | High | Extreme | High | Extreme | Extreme | Moderate | Little | Little | Moderate | High | Very little | Extreme | High | Extreme | Extreme | Extreme | Moderate | Moderate | High | Little | High | Timely delivery of materials, proper estimation of items of construction, non delay working are some of the major effective steps to control cost overrun | Same as before
9 | Girija Shankar Mohapatra | Owner | Ongoing | 37.72 crores | Building Projects | Yes | Yes | Extreme | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | High | Little | High | High | Extreme | Extreme | High | Extreme | High | Moderate | High | High | Extreme | High | Moderate | Extreme | High | Extreme | Extreme | Extreme | Extreme | High | Extreme | Moderate | High | High | Moderate | Little | Moderate | Very little | High | High | Moderate | Little | High | High | Moderate | Little | Little | Moderate | Due to advancement of technology and resources, we can make the use of good materials, skilled technical laborers, we should maintain a technical report in which the estimated cost and time of commencement add well as time of completion of the project is clearly mentioned.
10 | Rashmi Rani Mohapatra | Owner | Completed | 46 crores | Building Projects | Yes | Yes | Extreme | High | High | Extreme | Extreme | High | Extreme | Extreme | Moderate | Little | High | Extreme | Extreme | Moderate | High | Moderate | Moderate | Moderate | Extreme | High | Extreme | High | High | Little | Moderate | High | Moderate | Extreme | High | Extreme | Extreme | Extreme | High | High | Extreme | High | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | Moderate | High | Extreme | Little | Extreme | A good planning and maintenance of materials and all resources, a proper strategy must be prepared to overcome the cost overrun in firms.
11 | Chitta Ranjan Dash | Contractor | Completed | 2.65 Lakhs | Water Resource Projects | Yes | Yes | Moderate | High | Extreme | High | Extreme | Extreme | High | High | High | Extreme | High | High | Moderate | Extreme | Extreme | High | Extreme | Extreme | Moderate | Moderate | Extreme | Extreme | Moderate | Very little | Moderate | Little | Extreme | High | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | Extreme | Extreme | Moderate | Moderate | High | Extreme | Moderate | Extreme | High | Moderate | Little | High | Extreme | A proper planning and designs of the structure to be constructed is important. The estimated cost of the construction along with necessary precautions are also necessary for the safety of workers and also to tackle overrun.
12 | Paritosh Jena | Contractor | Ongoing | 32 crores | Water Resource Projects | Yes | Yes | High | Extreme | High | High | Extreme | Extreme | Extreme | Extreme | Moderate | High | Extreme | High | Extreme | Moderate | Little | High | Extreme | Extreme | High | Extreme | Extreme | Extreme | High | Extreme | High | Extreme | Extreme | High | High | Moderate | High | Moderate | Little | High | High | Extreme | Extreme | Little | Extreme | High | Extreme | Moderate | Extreme | High | High | Moderate | Moderate | Extreme | The supervisors must check the progress of the project at regular intervals. We must encourage the fellow laborers to give their best and should keep them away from idleness as this can seriously affect the completion of a project. | Same
13 | Rama Ballav Swain | Owner | Ongoing | 180 crores | Building Projects | Yes | Yes | High | Extreme | Extreme | Extreme | High | High | Extreme | Extreme | Extreme | Little | High | Extreme | Moderate | Extreme | High | Extreme | Extreme | Extreme | High | High | High | High | Moderate | High | High | Extreme | Extreme | Extreme | Moderate | Little | Moderate | High | High | Extreme | Extreme | High | Extreme | Moderate | Extreme | Extreme | Extreme | High | Extreme | Moderate | High | Little | High | Extreme | 1. We should plan and manage our resources according to the need of the project, 2. Tasks must be scheduled and organized in a strintgent manner, and 3.Control scope creep and optimize resources.
14 | Hrudananda Majhi | Consultant | Completed | 15 | Building Projects | Yes | No | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Little | Little | Very little | Very little | Little | Little | Little | Very little | Little | Little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Little | Very little | The projects should complete with in time period | Completed as per stipulated time
15 | Manas Ranjan Samal | Contractor | Completed | 11 crores | Road Projects | Yes | Yes | Moderate | Moderate | Extreme | Extreme | High | Moderate | Moderate | High | Moderate | Moderate | High | Extreme | High | Moderate | High | Moderate | Moderate | High | High | Moderate | High | Moderate | Moderate | Moderate | Moderate | High | High | High | Extreme | High | High | High | Moderate | High | Moderate | High | High | Moderate | Moderate | High | High | Extreme | Extreme | Extreme | Extreme | High | High | High | Project management Material management Manpower management Equipment management Time management And finance management are the key features to overcome the cost overrun. | Steps should be taken to complete the project within the stipulated timeline with proper management.
16 | Jagat kumar swain | Consultant | Completed | 5crores | Building Projects | Yes | Yes | Little | Very little | Very little | Little | Moderate | Moderate | Little | Little | Very little | Very little | Little | Little | Little | Moderate | Moderate | Little | Very little | Moderate | Moderate | Very little | Very little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Little | Little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Moderate | Moderate | Little | Very little | Very little | Very little | Very little | Little | Very little | Proper coordination between the owner with construction company and structural consultant
17 | Ankit nayak | Owner | Completed | 18000000 | Building Projects | Yes | Yes | Extreme | Very little | Very little | Moderate | Moderate | Little | Very little | High | Extreme | Little | Extreme | High | Little | Very little | High | Little | Moderate | High | Little | Very little | Extreme | Little | Very little | Moderate | Little | Moderate | High | Moderate | High | Moderate | Extreme | High | Little | Very little | Moderate | Very little | Moderate | High | Little | High | High | High | Little | Extreme | Extreme | Moderate | Moderate | High | Deal with clients and mutually solved the problem and strong management
18 | kanha Dash | Contractor | Completed | 272000 | Building Projects | Yes | Yes | Little | Very little | Very little | Very little | Moderate | Very little | Very little | Little | Very little | Very little | Little | Very little | Moderate | Very little | Little | Very little | Very little | Very little | Very little | Very little | Little | Moderate | Very little | Little | Little | Little | Moderate | Little | Extreme | Little | Very little | Very little | Very little | Little | Little | Very little | Very little | Very little | High | Moderate | Extreme | Moderate | Moderate | Little | Extreme | Moderate | High | Very little | any sort of expense that pushes a project past the agreed-upon budget. | This is due to bad estimates, or not enough data being collected when formulating the budget.
19 | RAMA KRISHNA BISWAL | Owner | Completed | 6,00,00,000/- | Building Projects | Yes | Yes | Very little | Little | High | Very little | Little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | High | Very little | Very little | Very little | Final Construction drawings released in time, alteration in design minimized. | All requirements should be finalized before commencement of construction, according to the requirement construction drawings to be prepared and should be released to the contractor in time. Particularly in industrial projects lot of modification comes from other interlinked sections. So to comply these demands drawings amended during progress of work.
20 | Rajan Patel | Contractor | Ongoing | 1.00 cr | Railway Projects | No | No | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | NA
21 | RAMA KRISHNA BISWAL | Owner | Completed | 2.2 CRORE | Water Resource Projects | Yes | Yes | Very little | Little | Moderate | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | High | Very little | Very little | Very little | Very little | Very little | Very little | ADDITIONAL WORK RESTRICTED TO MINIMUM REQUIRED QUANTITY. | SCOPE OF WORK SHOULD BE FINALIZED DURING ADMINISTRATIVE APPROVAL STAGE, ACCORDINGLY SCHEDULE OF QUANTITY SHOULD BE PREPARED, SO THAT ADDITIONAL WORK CAN BE MINIMIZED.
22 | Asish samantaray | Consultant | Ongoing |  | Building Projects | No | No | High | Very little | Very little | Very little | Little | High | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Moderate | Little | Little | Moderate | Moderate | Moderate | Little | Little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Very little | NA | NA
23 | Satyabrata mahalik | Consultant | Ongoing | Dont Know | Building Projects | No | No | Little | Very little | Little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Little | Little | Moderate | Little | Very little | Little | Very little | Very little | Little | Little | Very little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Little | Very little | Little | Little | Very little | Little | Little | Little | Very little | Little | Very little | Very little | NA | NA
24 | Satyashiva Dash | Consultant | Ongoing | 322.34 Cr | Water Resource Projects | No | Yes | Very little | Very little | Very little | Little | Little | Very little | Moderate | Little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Moderate | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | High | Little | High | Moderate | Little | Little | Little | Very little | Little | Very little | Very little | Little | Very little | Little | Little | Little | Little | Very little | Little | Very little | Little | Very little | To Avoid Unskilled Labour | Labour should be skilled
25 | Swagat Kumar Dash | Consultant | Completed | 1.39cr | Water Resource Projects | No | No | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Little | Very little | Little | Little | High | Little | Little | Very little | Very little | Very little | Little | Very little | Little | Moderate | Very little | Extreme | Little | Moderate | Little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Moderate | Very little | Little | Very little | Moderate | Little | Moderate | Moderate | Very little | High | Very little | NA | NA
26 | Biswajit Mohapatra | Consultant | Ongoing | 423.27cr | Building Projects | No | No | Moderate | Moderate | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Moderate | Very little | Moderate | Very little | Little | Very little | Little | Very little | Very little | Very little | Little | Little | High | Moderate | High | Very little | Very little | Moderate | Moderate | Moderate | Very little | Very little | Very little | Very little | Moderate | Little | Very little | Little | Moderate | Very little | Moderate | Little | Very little | Very little | Thorough Project Planning. The best way to stop cost overrun is to plan against it before executing a project. ... | Quality and keeping to a schedule can all go out the window if the project is delivered over-budget.
27 | SANDEEP LASKAR | Consultant | Ongoing | 423 cr | Building Projects | No | No | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Little | Very little | Very little | Very little | Very little | Very little | Little | Little | Very little | Little | Very little | Very little | High | Very little | High | Little | Very little | Very little | Little | Little | Very little | Very little | Very little | Very little | Moderate | Extreme | Very little | Very little | Very little | Very little | Moderate | Very little | High | Little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
28 | A K Mahapatra | Contractor | Ongoing | 900000 | Building Projects | No | No | Moderate | Very little | Very little | Little | Little | Very little | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Extreme | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
29 | BHIKARI PRADHAN | Contractor | Ongoing | 700000 | Others | No | No | Very little | Very little | Very little | Very little | Little | Very little | Little | Very little | Very little | Little | Little | Very little | Moderate | Very little | Very little | Moderate | Very little | Very little | Very little | Little | Little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Moderate | Moderate | Very little | Very little | Moderate | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | Very little | The best way ti stop cost overrun is a plan against it before executing a project | Throughly plan your project ahead of time
30 | Pritam Bidhar | Contractor | Ongoing | 8000000 | Building Projects | No | No | Little | Little | Moderate | Little | Moderate | Moderate | Little | Little | Moderate | Little | Moderate | Little | Little | Moderate | Little | Little | Moderate | Little | Moderate | Little | Moderate | Moderate | Moderate | Moderate | Little | Moderate | Moderate | Moderate | Little | Moderate | Little | Moderate | Little | Little | Moderate | Little | Moderate | Little | Moderate | Little | Moderate | Little | Moderate | Moderate | Little | Moderate | Little | Moderate | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
31 | S K Patra | Contractor | Ongoing | 6,00,00,000 | Bridge Projects | Yes | Yes | Moderate | Very little | High | Moderate | Extreme | Extreme | Extreme | Little | Moderate | Very little | Very little | Very little | Extreme | Extreme | Extreme | Extreme | High | Little | Little | High | Extreme | Little | Extreme | Very little | Very little | Extreme | Extreme | Extreme | Extreme | Little | Moderate | High | Little | Moderate | Very little | Extreme | Extreme | Extreme | Extreme | Extreme | Little | Extreme | Little | Moderate | Extreme | Little | High | High | The best way to stop cost overrun is to plan against it before executing a project. Proper cost management. Hiring a good project manager. | Thoroughly plan your project ahead of time
32 | Amlan Tarai | Contractor | Ongoing | 16.86 cr | Building Projects | No | No | Little | Very little | Very little | Very little | Moderate | Little | High | Moderate | Little | Very little | Little | Very little | Moderate | Very little | Very little | Little | Very little | Moderate | Very little | Moderate | Moderate | Moderate | Little | Little | Little | Moderate | Little | Moderate | Moderate | Little | Little | Little | Very little | Moderate | Moderate | Little | High | Moderate | High | High | Moderate | High | High | Moderate | Little | Very little | Little | Little | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time

## Sheet2
| Name | Related to | Status of the project | Total expected cost of the Project | Type of the Project | Have you come across cost overrun during handling any construction project? | Does the cost overrun delays the project? | mention causes of cost over run of your project and its impact [Improper cash inflow and outflow] | mention causes of cost over run of your project and its impact [Errors in designs] | mention causes of cost over run of your project and its impact [Delays in analysis & alteration in designs] | mention causes of cost over run of your project and its impact [Mismatch of ongoing construction with the actual plan] | mention causes of cost over run of your project and its impact [Increase in the cost of project] | mention causes of cost over run of your project and its impact [Conflict between owner and contractor] | mention causes of cost over run of your project and its impact [Changes in soil characteristics, at the time of construction] | mention causes of cost over run of your project and its impact [Incorrect Estimate] | mention causes of cost over run of your project and its impact [If owner is not financially viable] | mention causes of cost over run of your project and its impact [Issues relating to frauds and miscreants] | mention causes of cost over run of your project and its impact [Poor construction strategy] | mention causes of cost over run of your project and its impact [Poor site management] | mention causes of cost over run of your project and its impact [Enhancement in the cost of labourers] | mention causes of cost over run of your project and its impact [Unusual payment to labourers] | mention causes of cost over run of your project and its impact [Improper control of finance] | mention causes of cost over run of your project and its impact [Improper communication between owner and the contractor] | mention causes of cost over run of your project and its impact [Conflict on differentiating and biasing in between labourers] | mention causes of cost over run of your project and its impact [Improper material management and procurement] | mention causes of cost over run of your project and its impact [Accident due to faulty equipment] | mention causes of cost over run of your project and its impact [Non-availability of authorized (IS marked) machineries] | mention causes of cost over run of your project and its impact [Sudden fall of demand of a particular material in the market] | mention causes of cost over run of your project and its impact [Delivery of faulty machineries] | mention causes of cost over run of your project and its impact [Idle mindset of labourers] | mention causes of cost over run of your project and its impact [Improper maintenance of equipment] | mention causes of cost over run of your project and its impact [Changes in materials and labour] | mention causes of cost over run of your project and its impact [Demand of 4 prices by group of labourers] | mention causes of cost over run of your project and its impact [Rise and fall in prices of material] | mention causes of cost over run of your project and its impact [Failure of equipment at the time of construction] | mention causes of cost over run of your project and its impact [Price hike of materials] | mention causes of cost over run of your project and its impact [Hiring of unskilled labourers] | mention causes of cost over run of your project and its impact [Improper technical performance] | mention causes of cost over run of your project and its impact [Lack of technical assistance from the government] | mention causes of cost over run of your project and its impact [Wastes rising from construction materials] | mention causes of cost over run of your project and its impact [Existing demand in market] | mention causes of cost over run of your project and its impact [Less availability of living and food arrangements for labors.] | mention causes of cost over run of your project and its impact [Inadequate materials] | mention causes of cost over run of your project and its impact [Improper use of resources] | mention causes of cost over run of your project and its impact [Worker’s problems] | mention causes of cost over run of your project and its impact [Sudden increase in price of commodities] | mention causes of cost over run of your project and its impact [Less availability of time (time uncertainties).] | mention causes of cost over run of your project and its impact [Inaccurate project cost, which leads to confusion.] | mention causes of cost over run of your project and its impact [New additional works, which gave rise to increased problems] | mention causes of cost over run of your project and its impact [Problems pertaining to environmental clearance] | mention causes of cost over run of your project and its impact [Unpredictable circumstances (flood, cyclone, earthquake etc)] | mention causes of cost over run of your project and its impact [COVID-19 pandemic] | mention causes of cost over run of your project and its impact [Levies or taxes charged by the agencies] | mention causes of cost over run of your project and its impact [Local people/political interference] | mention causes of cost over run of your project and its impact [Unsuitable weather conditions] | What are the steps taken to over come the cost overrun? | Any suggestion to overcome the cost overrun
1 | Pinky Nayak | Owner | Ongoing | 738 crores | Railway Projects | Yes | Yes | 5 | 2 | 3 | 3 | 4 | 3 | 4 | 5 | 5 | 1 | 2 | 2 | 4 | 4 | 5 | 5 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 3 | 5 | 1 | 1 | 3 | 4 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 4 | 3 | 5 | 3 | 4 | 5 | 5 | 5 | 4 | 4 | 3 | 4 | 1.A proper management of materials, laborers and finance, 2. Completing the project within a stipulated time and cost, 3. Abiding to laws and regulations as proposed by the government. | Same as above.
2 | Vikash Pattnaik | Contractor | Completed | 17.44 lakhs | Bridge Projects | Yes | Yes | 5 | 4 | 4 | 5 | 5 | 5 | 2 | 5 | 4 | 5 | 4 | 1 | 1 | 3 | 4 | 2 | 3 | 4 | 5 | 5 | 1 | 2 | 3 | 5 | 4 | 3 | 5 | 1 | 3 | 1 | 2 | 2 | 4 | 5 | 4 | 3 | 5 | 2 | 5 | 2 | 4 | 1 | 5 | 3 | 5 | 4 | 3 | 5 | A combined trail should be proposed by the contractor to take Care of all the problems likely to happen in a project. | Same as above.
3 | Kali Prasad Mishra | Contractor | Completed | 67 crores | Building Projects | Yes | Yes | 3 | 5 | 3 | 2 | 5 | 5 | 5 | 4 | 5 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 5 | 3 | 4 | 5 | 5 | 1 | 4 | 3 | 4 | 5 | 5 | 1 | 1 | 1 | 3 | 4 | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 1 | 5 | 3 | 5 | 2 | 4 | 4 | A significant study suggests that, cost overrun mainly occurs due to all the above defined problem. We can make good choices of materials, laborers, have a good attitude and strategy towards the project and should try our best to complete the project within a given time, irrespective of conditions.
4 | Ankita Sahu | Contractor | Ongoing | 43.87 crores | Building Projects | Yes | Yes | 3 | 4 | 5 | 2 | 2 | 5 | 4 | 5 | 4 | 1 | 2 | 4 | 5 | 5 | 3 | 4 | 5 | 3 | 5 | 3 | 5 | 5 | 4 | 5 | 2 | 4 | 3 | 4 | 5 | 5 | 2 | 1 | 4 | 3 | 4 | 5 | 5 | 2 | 4 | 4 | 5 | 1 | 4 | 3 | 5 | 1 | 3 | 2 | New as well as good quality of materials should be hired. Skilled laborers with sound technical knowledge are also important for a successful completion of project.
5 | Pramod Kumar Mohanty | Contractor | Ongoing | 44 crores | Building Projects | Yes | Yes | 3 | 4 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 2 | 4 | 3 | 2 | 5 | 5 | 3 | 4 | 2 | 5 | 5 | 4 | 5 | 4 | 5 | 5 | 3 | 4 | 4 | 5 | 5 | 5 | 3 | 1 | 3 | 1 | 5 | 4 | 1 | 5 | 4 | 5 | 3 | 5 | 4 | 3 | 2 | 3 | 4 | A cost-effective planning as well as a good construction method is required to reduce the bad effect of cost overrun.
6 | Bhabani Prasad Mishra | Owner | Ongoing | 58 crores | Building Projects | Yes | Yes | 4 | 5 | 5 | 5 | 5 | 3 | 4 | 5 | 5 | 1 | 3 | 2 | 4 | 3 | 4 | 2 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 4 | 5 | 5 | 5 | 4 | 5 | 2 | 1 | 3 | 3 | 4 | 5 | 5 | 2 | 5 | 4 | 5 | 1 | 5 | 4 | 4 | 2 | 3 | 3 | A careful selection of work site, materials, equipments and labor is required to reduce cost overrun. Proper flow of cash and words of encouragement to the laborers are also effective tools for reducing the loss to the organization. | Same as previous.
7 | Sashikanta Dash | Owner | Ongoing | 38 crores | Building Projects | Yes | Yes | 5 | 4 | 5 | 5 | 4 | 3 | 4 | 5 | 5 | 2 | 5 | 3 | 3 | 4 | 5 | 4 | 3 | 2 | 5 | 5 | 5 | 4 | 3 | 4 | 2 | 3 | 4 | 4 | 5 | 5 | 1 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 4 | 4 | 5 | 3 | 5 | 4 | 4 | 2 | 4 | 2 | As reconstruction of a structure is a difficult process, so we should be very careful while executing the constructional as well as aesthetical works. The main plan to avoid cost overrun should be a good planning and engagement of all resources and materials. | First, we should make the use of natural and locally available resources to get rid of extra cost of materials. Secondly, we should act by the laws given by government to safeguard our project from penalty.
8 | Suresh Mohan Routray | Contractor | Ongoing | 66.73 crores | Building Projects | Yes | Yes | 3 | 4 | 5 | 5 | 5 | 3 | 4 | 5 | 4 | 4 | 5 | 5 | 1 | 3 | 3 | 4 | 4 | 5 | 5 | 4 | 5 | 3 | 4 | 5 | 5 | 5 | 4 | 4 | 5 | 4 | 5 | 5 | 3 | 2 | 2 | 3 | 4 | 1 | 5 | 4 | 5 | 5 | 5 | 3 | 3 | 4 | 2 | 4 | Timely delivery of materials, proper estimation of items of construction, non delay working are some of the major effective steps to control cost overrun | Same as before
9 | Girija Shankar Mohapatra | Owner | Ongoing | 37.72 crores | Building Projects | Yes | Yes | 5 | 4 | 5 | 3 | 5 | 4 | 5 | 5 | 4 | 2 | 4 | 4 | 5 | 5 | 4 | 5 | 4 | 3 | 4 | 4 | 5 | 4 | 3 | 5 | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 3 | 4 | 4 | 3 | 2 | 3 | 1 | 4 | 4 | 3 | 2 | 4 | 4 | 3 | 2 | 2 | 3 | Due to advancement of technology and resources, we can make the use of good materials, skilled technical laborers, we should maintain a technical report in which the estimated cost and time of commencement add well as time of completion of the project is clearly mentioned.
10 | Rashmi Rani Mohapatra | Owner | Completed | 46 crores | Building Projects | Yes | Yes | 5 | 4 | 4 | 5 | 5 | 4 | 5 | 5 | 3 | 2 | 4 | 5 | 5 | 3 | 4 | 3 | 3 | 3 | 5 | 4 | 5 | 4 | 4 | 2 | 3 | 4 | 3 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 3 | 5 | 4 | 5 | 5 | 3 | 4 | 5 | 2 | 5 | A good planning and maintenance of materials and all resources, a proper strategy must be prepared to overcome the cost overrun in firms.
11 | Chitta Ranjan Dash | Contractor | Completed | 2.65 Lakhs | Water Resource Projects | Yes | Yes | 3 | 4 | 5 | 4 | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 3 | 5 | 5 | 4 | 5 | 5 | 3 | 3 | 5 | 5 | 3 | 1 | 3 | 2 | 5 | 4 | 4 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 4 | 5 | 3 | 5 | 4 | 3 | 2 | 4 | 5 | A proper planning and designs of the structure to be constructed is important. The estimated cost of the construction along with necessary precautions are also necessary for the safety of workers and also to tackle overrun.
12 | Paritosh Jena | Contractor | Ongoing | 32 crores | Water Resource Projects | Yes | Yes | 4 | 5 | 4 | 4 | 5 | 5 | 5 | 5 | 3 | 4 | 5 | 4 | 5 | 3 | 2 | 4 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 5 | 4 | 4 | 3 | 4 | 3 | 2 | 4 | 4 | 5 | 5 | 2 | 5 | 4 | 5 | 3 | 5 | 4 | 4 | 3 | 3 | 5 | The supervisors must check the progress of the project at regular intervals. We must encourage the fellow laborers to give their best and should keep them away from idleness as this can seriously affect the completion of a project. | Same
13 | Rama Ballav Swain | Owner | Ongoing | 180 crores | Building Projects | Yes | Yes | 4 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 5 | 2 | 4 | 5 | 3 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 5 | 5 | 5 | 3 | 2 | 3 | 4 | 4 | 5 | 5 | 4 | 5 | 3 | 5 | 5 | 5 | 4 | 5 | 3 | 4 | 2 | 4 | 5 | 1. We should plan and manage our resources according to the need of the project, 2. Tasks must be scheduled and organized in a strintgent manner, and 3.Control scope creep and optimize resources.
14 | Hrudananda Majhi | Consultant | Completed | 15 | Building Projects | Yes | No | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | The projects should complete with in time period | Completed as per stipulated time
15 | Manas Ranjan Samal | Contractor | Completed | 11 crores | Road Projects | Yes | Yes | 3 | 3 | 5 | 5 | 4 | 3 | 3 | 4 | 3 | 3 | 4 | 5 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | Project management Material management Manpower management Equipment management Time management And finance management are the key features to overcome the cost overrun. | Steps should be taken to complete the project within the stipulated timeline with proper management.
16 | Jagat kumar swain | Consultant | Completed | 5crores | Building Projects | Yes | Yes | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | Proper coordination between the owner with construction company and structural consultant
17 | Ankit nayak | Owner | Completed | 18000000 | Building Projects | Yes | Yes | 5 | 1 | 1 | 3 | 3 | 2 | 1 | 4 | 5 | 2 | 5 | 4 | 2 | 1 | 4 | 2 | 3 | 4 | 2 | 1 | 5 | 2 | 1 | 3 | 2 | 3 | 4 | 3 | 4 | 3 | 5 | 4 | 2 | 1 | 3 | 1 | 3 | 4 | 2 | 4 | 4 | 4 | 2 | 5 | 5 | 3 | 3 | 4 | Deal with clients and mutually solved the problem and strong management
18 | kanha Dash | Contractor | Completed | 272000 | Building Projects | Yes | Yes | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 3 | 2 | 5 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 3 | 3 | 2 | 5 | 3 | 4 | 1 | any sort of expense that pushes a project past the agreed-upon budget. | This is due to bad estimates, or not enough data being collected when formulating the budget.
19 | RAMA KRISHNA BISWAL | Owner | Completed | 6,00,00,000/- | Building Projects | Yes | Yes | 1 | 2 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | Final Construction drawings released in time, alteration in design minimized. | All requirements should be finalized before commencement of construction, according to the requirement construction drawings to be prepared and should be released to the contractor in time. Particularly in industrial projects lot of modification comes from other interlinked sections. So to comply these demands drawings amended during progress of work.
20 | Rajan Patel | Contractor | Ongoing | 1.00 cr | Railway Projects | No | No | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | NA
21 | RAMA KRISHNA BISWAL | Owner | Completed | 2.2 CRORE | Water Resource Projects | Yes | Yes | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | ADDITIONAL WORK RESTRICTED TO MINIMUM REQUIRED QUANTITY. | SCOPE OF WORK SHOULD BE FINALIZED DURING ADMINISTRATIVE APPROVAL STAGE, ACCORDINGLY SCHEDULE OF QUANTITY SHOULD BE PREPARED, SO THAT ADDITIONAL WORK CAN BE MINIMIZED.
22 | Asish samantaray | Consultant | Ongoing |  | Building Projects | No | No | 4 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | NA | NA
23 | Satyabrata mahalik | Consultant | Ongoing | Dont Know | Building Projects | No | No | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | NA | NA
24 | Satyashiva Dash | Consultant | Ongoing | 322.34 Cr | Water Resource Projects | No | Yes | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 2 | 4 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | To Avoid Unskilled Labour | Labour should be skilled
25 | Swagat Kumar Dash | Consultant | Completed | 1.39cr | Water Resource Projects | No | No | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 4 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 5 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 4 | 1 | NA | NA
26 | Biswajit Mohapatra | Consultant | Ongoing | 423.27cr | Building Projects | No | No | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 4 | 3 | 4 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | Thorough Project Planning. The best way to stop cost overrun is to plan against it before executing a project. ... | Quality and keeping to a schedule can all go out the window if the project is delivered over-budget.
27 | SANDEEP LASKAR | Consultant | Ongoing | 423 cr | Building Projects | No | No | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 4 | 1 | 4 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 1 | 3 | 1 | 4 | 2 | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
28 | A K Mahapatra | Contractor | Ongoing | 900000 | Building Projects | No | No | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
29 | BHIKARI PRADHAN | Contractor | Ongoing | 700000 | Others | No | No | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | The best way ti stop cost overrun is a plan against it before executing a project | Throughly plan your project ahead of time
30 | Pritam Bidhar | Contractor | Ongoing | 8000000 | Building Projects | No | No | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 2 | 3 | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
31 | S K Patra | Contractor | Ongoing | 6,00,00,000 | Bridge Projects | Yes | Yes | 3 | 1 | 4 | 3 | 5 | 5 | 5 | 2 | 3 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 4 | 2 | 2 | 4 | 5 | 2 | 5 | 1 | 1 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | 2 | 3 | 1 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 2 | 3 | 5 | 2 | 4 | 4 | The best way to stop cost overrun is to plan against it before executing a project. Proper cost management. Hiring a good project manager. | Thoroughly plan your project ahead of time
32 | Amlan Tarai | Contractor | Ongoing | 16.86 cr | Building Projects | No | No | 2 | 1 | 1 | 1 | 3 | 2 | 4 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 4 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 1 | 2 | 2 | The best way to stop cost overrun is to plan against it before executing a project | Thoroughly plan your project ahead of time
Very little(1) | [7 empty] | 6 | 13 | 12 | 10 | 4 | 11 | 10 | 9 | 13 | 17 | 10 | 14 | 9 | 12 | 8 | 8 | 10 | 8 | 12 | 12 | 9 | 9 | 11 | 12 | 9 | 9 | 8 | 9 | 5 | 7 | 11 | 11 | 11 | 8 | 11 | 11 | 11 | 12 | 8 | 6 | 8 | 10 | 7 | 10 | 6 | 12 | 7 | 12
2 | [7 empty] | 6 | 5 | 2 | 8 | 9 | 3 | 5 | 7 | 2 | 9 | 9 | 7 | 9 | 3 | 8 | 8 | 4 | 11 | 4 | 4 | 6 | 8 | 6 | 7 | 10 | 7 | 3 | 5 | 4 | 11 | 9 | 7 | 9 | 8 | 6 | 6 | 3 | 9 | 4 | 7 | 5 | 7 | 7 | 3 | 5 | 11 | 9 | 5 | 0 | 0
3 | [7 empty] | 10 | 2 | 4 | 4 | 5 | 7 | 3 | 1 | 6 | 2 | 2 | 2 | 6 | 9 | 4 | 6 | 9 | 5 | 3 | 5 | 3 | 5 | 8 | 4 | 4 | 7 | 4 | 5 | 4 | 5 | 4 | 7 | 6 | 8 | 7 | 5 | 4 | 8 | 6 | 3 | 4 | 6 | 3 | 10 | 7 | 4 | 7 | 3
4 | [7 empty] | 4 | 8 | 5 | 2 | 5 | 4 | 7 | 4 | 5 | 2 | 7 | 5 | 3 | 2 | 7 | 6 | 4 | 3 | 5 | 5 | 4 | 4 | 5 | 3 | 6 | 3 | 9 | 7 | 9 | 3 | 2 | 5 | 5 | 5 | 5 | 3 | 7 | 1 | 5 | 11 | 6 | 4 | 3 | 6 | 7 | 4 | 9 | 7
5 | [7 empty] | 6 | 4 | 9 | 8 | 9 | 7 | 7 | 11 | 6 | 2 | 4 | 4 | 5 | 6 | 5 | 4 | 5 | 5 | 8 | 6 | 10 | 6 | 2 | 6 | 3 | 6 | 8 | 6 | 10 | 6 | 6 | 2 | 1 | 3 | 3 | 7 | 7 | 2 | 9 | 5 | 9 | 5 | 12 | 3 | 7 | 1 | 0 | 5
[8 empty] | 58.75 | 50.625 | 58.125 | 53.75 | 63.75 | 55.625 | 57.5 | 60.625 | 53.125 | 36.875 | 51.25 | 46.25 | 51.25 | 51.875 | 55.625 | 53.75 | 53.75 | 51.25 | 55.625 | 53.125 | 60 | 53.75 | 48.125 | 50 | 50 | 53.75 | 63.75 | 57.5 | 69.375 | 53.75 | 49.375 | 47.5 | 45 | 51.875 | 49.375 | 53.125 | 57.5 | 42.5 | 61.875 | 61.25 | 61.875 | 51.875 | 63.75 | 53.125 | 62.5 | 41.875 | 51.25 | 52.5
[8 empty] | 58.75 | 50.625 | 58.125 | 53.75 | 63.75 | 55.625 | 57.5 | 60.625 | 53.125 | 36.875 | 51.25 | 46.25 | 51.25 | 51.875 | 55.625 | 53.75 | 53.75 | 51.25 | 55.625 | 53.125 | 60 | 53.75 | 48.125 | 50 | 50 | 53.75 | 63.75 | 57.5 | 69.375 | 53.75 | 49.375 | 47.5 | 45 | 51.875 | 49.375 | 53.125 | 57.5 | 42.5 | 61.875 | 61.25 | 61.875 | 51.875 | 63.75 | 53.125 | 62.5 | 41.875 | 51.25 | 52.5

## Sheet3
C1 | Improper cash inflow and outflow | 58.75
C2 | Errors in designs | 50.625
C3 | Delays in analysis & alteration in designs] | 58.125
C4 | Mismatch of ongoing construction with the actual plan] | 53.75
C5 | Increase in the cost of project] | 63.75
C6 | Conflict between owner and contractor] | 55.625
C7 | Changes in soil characteristics, at the time of construction] | 57.5
C8 | Incorrect Estimate] | 60.625
C9 | If owner is not financially viable] | 53.125
C10 | Issues relating to frauds and miscreants] | 36.875
C11 | Poor construction strategy] | 51.25
C12 | Poor site management] | 46.25
C13 | Enhancement in the cost of labourers] | 51.25
C14 | Unusual payment to labourers] | 51.875
C15 | Improper control of finance | 55.625
C16 | Improper communication between owner and the contractor] | 53.75
C17 | Conflict on differentiating and biasing in between labourers] | 53.75
C18 | Improper material management and procurement] | 51.25
C19 | Accident due to faulty equipment | 55.625
C20 | Non-availability of authorized (IS marked) machineries] | 53.125
C21 | Sudden fall of demand of a particular material in the market] | 60
C22 | Delivery of faulty machineries] | 53.75
C23 | Idle mindset of labourers] | 48.125
C24 | Improper maintenance of equipment] | 50
C25 | Changes in materials and labour] | 50
C26 | Demand of 4 prices by group of labourers] | 53.75
C27 | Rise and fall in prices of material] | 63.75
C28 | Failure of equipment at the time of construction] | 57.5
C29 | Price hike of materials] | 69.375
C30 | Hiring of unskilled labourers] | 53.75
C31 | Improper technical performance] | 49.375
C32 | Lack of technical assistance from the government] | 47.5
C33 | Wastes rising from construction materials] | 45
C34 | Existing demand in market] | 51.875
C35 | Less availability of living and food arrangements for labors.] | 49.375
C36 | Inadequate materials] | 53.125
C37 | Improper use of resources] | 57.5
C38 | Worker’s problems] | 42.5
C39 | Sudden increase in price of commodities] | 61.875
C40 | Less availability of time (time uncertainties).] | 61.25
C41 | Inaccurate project cost, which leads to confusion. | 61.875
C42 | New additional works, which gave rise to increased problems] | 51.875
C43 | Problems pertaining to environmental clearance] | 63.75
C44 | Unpredictable circumstances (flood, cyclone, earthquake etc)] | 53.125
C45 | COVID-19 pandemic] | 62.5
C46 | Levies or taxes charged by the agencies] | 41.875
C47 | Local people/political interference] | 51.25
C48 | Unsuitable weather conditions] | 52.5
What are the steps taken to over come the cost overrun?